## Question
Project Alphabet | GD | Singtel | Meeting on 07Apr16 | Meeting on 19Apr16
Design | 1. Work out the HTML based on Singtel design (will start HTML once design confirmed). | 1. Help to provide the mockup/design for desktop and mobile (the one we received looks like draft version). 2. The design should support responsive WEB. | Mockup for review: by 15Apr16 Final Design to start work on HTML template: End Apr'16 | Mockup already & waiting for review
Website | 1. Build a responsive WEB (support for desktop and mainly iOS and Android devices). | 1. Any sub-code page for this project? Currently Project Note has 1 Generic WEB (https://music.singtel.com/) and in future there will be sub-code page sit under this Generic WEB. | Might have sub-code page for promotional purpose (in future).
Domain |  | 1. Create Staging and Production URL. | Singtel will advise the URL link
Hosting | 1. GD will not able to help in system configuration and environment setup necessary action items due to the hosting is in Singtel. 2. GD can zip the file to Singtel for deployment. | 1. Host in Singtel. 2. Refer to Project Note, the environment is support PHP (version 5.3.3) Yii framework. | Options: i) In Singtel ii) Together with Music Service Note: Singtel will discuss with Music team & confirm it | GD to host (together with Project Note WEB) Any IP change, GD to confirm?
Login Method & Who can Login? |  | 1. Any OTP validation during login process? 2. Refer to Project Note, it is allow Singtel Postpaid customer to login. How about this project? 3. Any API for the login validation? i) Refer to Project Note, we are calling the NDP API. May need your help to check with Atomic/NDP that can we use the same API or the parameter should be use if calling the same API. OR ii) If use new API, please provide the API spec. 4. Can suggest the error message to be use if login failed / OTP incorrect / Resend OTP? | 1. Customer need to enter OTP & OTP validation during login (Singtel has to advise the shortcode, API to be use, SMS message content and this SMS send is using bizlive or NDP?). 2. OTP flow will follow Project Note. Example: frequencies to request OTP, how long need to key in OTP...etc. 3. Only Singtel Postpaid can login which is similar to Project Note. 4. Use the same API as Project Note for login validation. Singtel will confirm which API to be use and parameters to be use after check with Atomic. 5. GD will provide the error list to Singtel to advise error message should show in WEB. | 1. Use Bizlive, but Singtel will confirm the shortcide, API to be use and SMS message content.
Subscription |  | 1. Help to provide the product code & description. 2. Help to provide test number for GD testing in both Staging and Production. 3. Any subscription restriction (Example: Singtel Postpaid, Singtel Prepaid, Non-Singtel, Resubsribe, etc)? 4. Can suggest the success subscribed message and error message if failed to subscribe? 5. Any promotion in plan box? | 1. Estimated have 7 products selling in Alphabet WEB. Singtel will share the details. 2. Singtel need to provide Singtel Postpaid, Singtel Prepaid, Non-Singtel numbers for testing purpose. 3. Singtel will advise error message should show in WEB after review Atomic API Spec. 4. Set promotion period in plan box. Example, XX plan will be selling at $9.90 on Apr'16 and revert back to original plan (YY - $13.99) at 01May'16.
Charging |  | 1. Any API to use for Charging? i) Refer to Project Note, we are calling the Atomic Charging API (Authorize API and Report Delivery Status API). May need your help to check with Atomic/NDP that can we use the same API or the parameter should be use if calling the same API. OR ii) If use new API, please provide the API spec. | 1. Use the same API as Project Note for Charging. Singtel will confirm which API to be use and parameters to be use after check with Atomic. 2. Singtel can ask the call flow from Atomic? 3. Charging checking will be handle by Atomic which is same as Project Note. | 1. Atomic will confirm the call flow 2. Call Authorize Purchase API > RDS API (Atomic will send GD the new login ID, by22Apr16) 3. Atomic will share the parameters 4. Clean Profile in Staging -> seek help from Atomic
Activation SMS |  | 1. Once successfully subscribed, Singtel may need to send SMS to customer. | Need Activation SMS after subscribed to the plan (Singtel has to advise the shortcode, API to be use, SMS message content and this SMS send is using bizlive or NDP?) - Currently in Project Note, GD only send the SMS for AMPed subscriber but then the KKBOX and Spotify subscriber is handle by other party. Can Singtel confirm this? | Atomic will send the SMS
Provision in GD / Transaction History | 1. GD will not keep any subscription record / data |  | No provisioning in GD side | Atomic will keep the record
Log |  | 1. Can we identify what item need to be keep as log? 2. Can advise where to store? Note: The log can use for troubleshooting purpose. | Singtel will confirm log is require or not? | GD will keep the log (follow project note)
Staging |  | 1. Refer to Project Note, we are calling Atomic Staging UAT (NDP UAT IP is 203.127.145.27). So, may need your help check with Atomic that GD should call Atomic Staging UAT or ECO due to Atomic has 2 Staging environments. 2. And the IP address is? | Singtel will check with Atomic about Staging environment | NDP Staging UAT (end .27)
Resubscribe |  | 1. Refer to Project Note, customer is able to see the plan while he has subscribed before (example, he has subscribed kkbox, if he go back to landing page, he manage to see kkbox plan box. And he can go resubscribe the same plan but Atomic will perform checking and return GD some error code & message when GD call Atomic charging API). How about this project, or follow Project Note?
Unsubscription |  | 1. Refer to Project Note, unsubscribe service is not exist to Customer. | Unsubscription service is not exist in WEB
Reporting | 1. GD will not able to generate report because the data is not store in GD side. |  |  | Singtel will get the report from Atomic
Tagging |  | 1. Any tagging embed to this WEB? Refer to Project Note, we have implement Havas Tags in every single page and we have create GTM for Singtel. 2. Do you need SEO (Currently we have implement SEO in Landing Page for Project Note) | 1. Singtel has to provide the hava tags script to GD to implement (could be similar to Project Note). 2. Singtel has to provide the account details for GD to create the GTM. 3. Singtel will engage with tagging team about the GA. 4. Please share the SEO details if this is require.
Promo Banner |  | 1. Any promotion section? Or have promo banner? | 1. Singtel will share the rotating banner design / banner requirement. 2. Maximum = 5 promo banners 3. If there is no banner exist, then will hide the banner section. 4. This can be deliver by End July'16.
FAQ |  | 1. To provide the FAQ copy if any | Singtel will share FAQ copy
T&C |  | 1. To provide the T&C copy if any | Singtel will share T&C copy
SSL certificate |  | 1. Refer to Project Note, the website is using https. How about this project? | Singtel has to purchase the certificate if needed https
CMS manage banner | 1. GD can help to develop the CMS for Singtel to manage the promo banner |  | 1. GD will develop CMS for Singtel to manage the promo banner. 2. Singtel to advise the banner design / requirements for assessment purpose. 3. This can be deliver by End July'16.
Others
Singtel Shop and SPEAR | 1. Should be not involving GD? |  | Is not involve GD
Launch date |  |  | Target date: Soft launch is Mid-June'16
Project Management | √
Design |  | √
HTML | √
Development | √
Deployment |  | √
Testing | √ | √